Risk Register

Researcher Productivity Analysis Tool — G8 Research Output Database

CITS3200 Professional Computing — Group 20 — Sprint 1

# 1. How risks are scored

Each risk is rated Low, Medium, High or Critical, judged on how likely it is to happen and how much damage it would do if it did.

Risks are listed most serious first. Anything rated High or Critical is reviewed at the weekly team meeting.

# 2. Risk register

| ID | Risk | Category | Rating | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Publications are attributed to the wrong academic through name-matching error. The system names individuals, so mistakes are visible. | Data | Critical | Match on DOI first and require the institution to agree. Hand-check a sample and publish the measured error rate. Flag uncertain matches rather than asserting them. |
| R2 | The full scope cannot be delivered within the team's 360 hours. | Schedule | Critical | Staged delivery with a minimum acceptable product agreed with the client. Hours tracked weekly against budget and scope reduced by agreement, not by silent failure. |
| R3 | A critical skill is held by only one person, who becomes overloaded and a single point of failure. | Team | Critical | No part of the system is owned by one person. Each major component is worked on by at least two members, and every significant change is reviewed by someone other than its author. Prefer widely known technology over anything only one person understands. |
| R4 | A university changes its website, or blocks collection, and the pipeline stops working. | Data | High | Keep each university's parsing in its own module so one break does not affect the others. Log failures per source without aborting the run. Honour robots.txt and rate-limit requests. |
| R5 | Institutional repositories have no usable interface, or their coverage of accounting and finance is incomplete. | Data | High | Audit every repository and test-harvest one before committing to the approach. Fall back to OpenAlex and profile-page scraping, and record the limitation. |
| R6 | The data collected is already out of date. UQ publication listings were found ending at 2024. | Data | High | Use repositories rather than profile pages as the main publication source, and display the last harvest date and latest publication year for each source (FR14). |
| R7 | Assessment load in other units during Weeks 10 to 12 reduces the hours available at the critical point. | Schedule | High | Front-load development so feature work is finished by Week 10, leaving the last weeks for testing, documentation and deployment. |
| R8 | The learning curve on unfamiliar technology is underestimated, particularly repository harvesting and record matching. | Team | High | Prove each unfamiliar technology with a short, time-boxed spike before relying on it, and do this in Weeks 3 and 4 rather than deferring it. Whoever learns something new writes up what they found in the repository so nobody else starts from zero. |
| R9 | A team member becomes unavailable through illness, misadventure or withdrawal. | Team | High | All work committed to the repository rather than held on one machine. Pairing on critical components. Difficulties reported to the auditor early rather than late. |
| R10 | Re-running the pipeline duplicates records or loses data. | Technical | High | Use the uniqueness keys defined in the Scope of Work. Test the refresh by running it twice and checking the database is unchanged. |
| R11 | The volume of collection is underestimated. The reference system holds around 539 researchers with full publication histories. | Schedule | High | Measure how long the first university takes and extrapolate before committing to all eight. Staged delivery means a subset is completed first. |
| R12 | The ABDC journal list, or impact factor data if obtained, is committed to the repository. The repository is public, so this would republish a dataset the team does not own. | Compliance | High | Add data file patterns to .gitignore before any data is downloaded and load the list from a local path documented in the installation guide. Show individual journal rankings rather than republishing the list. Because the repository is public and a committed file stays in the history even after deletion, prevention is the only effective control. |
| R13 | The intellectual property model has not been confirmed. The repository is public, so if a model applies that restricts distribution, work has already been published. | Compliance | High | Confirm the model with the client at the next meeting; two of the five models used in this unit would prohibit public release. Until it is confirmed, keep out of the repository anything that could not be withdrawn, and be ready to make it private at short notice. |
| R14 | Journal matching maps a publication to the wrong journal, giving it an incorrect ranking. | Data | Medium | Join on ISSN first and fall back to title matching only at a high threshold. Log every unmatched or low-confidence journal for review. |
| R15 | The client requests additions during the project that displace committed work. | Schedule | Medium | Assess every change against the hours remaining before accepting it, and minute the decision. |
| R16 | Where the system will be hosted is not confirmed, compressing all deployment work into Sprint 3. | Schedule | Medium | Press for a decision at the next client meeting. Keep deployment simple and environment-independent so the target can be chosen late. |
| R17 | Unattended automated updating is not achieved, as happened to the previous team. | Schedule | Medium | Already written into the Scope of Work as a best-effort objective rather than a commitment. The committed deliverable is an on-demand refresh. |
| R18 | Impact factor data is licensed and access is unconfirmed. | Data | Medium | The client has not asked for impact factor metrics, so only two optional measures are affected. They are written into the Scope of Work as conditional and withdrawn if access is not obtained. The ABDC journal rankings, which the client did ask for, are freely available. |
| R19 | Publishing ranked productivity data about named academics attracts objection. | Compliance | Medium | Use only information the universities already publish. Publish the methodology and its limitations, and provide a route for correcting errors. |